|  | Closeout Report: Tablet Rollout` |
| --- | --- |

# Project Summary

The Sauce & Spoon tablet rollout aimed to modernize the dining experience by introducing tablet-based ordering, payment, and customer engagement features. The project was launched successfully on April 23, meeting the planned schedule. Adjustments were made after the pilot test to improve navigation, reduce table turn times, and address technical issues. Overall, the rollout achieved its objectives of enhancing customer experience, increasing efficiency, and aligning with brand innovation.

# Methodology

- Conducted a test launch with 50 customers, followed by a detailed survey.

- Gathered feedback from both customers and waitstaff.

- Iteratively improved tablet navigation, payment messaging, and technical reliability.

- Implemented training programs for front-of-house (FOH) and back-of-house (BOH) staff.

- Collaborated with general managers to reduce table turn times and improve guest pacing.

- Established a pre-service testing checklist to minimize technical glitches.

# Results

Performance Baseline:

|  | Planned | Actual | Notes |
| --- | --- | --- | --- |
| Actual Project Schedule vs Planned | Launch on Apr. 23 | Launched on Apr. 23 | We were able to launch on the day we wanted, but had to accelerate our tasks due to delays |
| Actual Project Cost vs Planned | Training materials and fees: $10,000 Hardware and software implementation across locations: $3,500 Maintenance (IT fees): $5,000 Updated website and menu design fee: $5,000 Other customization fees: $550 | Training materials and fees: $7,486 Hardware and software implementation across locations: $3,600 annually Maintenance (IT fees): $0 (included with hardware order subscription) Updated website and menu design fee: $4,250 Other customization fees: $578 | Overall, we nearly matched our budget |
| Planned Scope vs Delivered Scope | Install tablets at two restaurant locations Launch at the beginning of Q2 (April 1) Create a plan for how to train staff on the new system | Physically installed tablets at two restaurant locations via electrician Added menus, coupons, branding, and additional content to tablets Integrated tablets with POS system Negotiated with tablet vendor over timing Created a plan for training Managed waitstaff expectations and concerns Trained BOH and FOH Created system for maintenance/locking Implemented system of surveying and measuring customer satisfaction | We didn’t realize how many moving pieces we were going to encounter |

Key Accomplishments:

 Successful on-time launch across two restaurant locations.

- Improved navigation layout based on pilot feedback, making tablets easier to use.

- Reduced table turn time by 30 minutes, leading to shorter wait times and increased guest throughput.

- Increased daily guest count by 20% at the Downtown location (goal was 10%).

- Reduced food waste by 25%, meeting sustainability targets.

- Achieved less than 5% weekly technical issues after implementing pre-service testing.

- Maintained checkout time at one minute or less, ensuring efficiency.

- Strong customer engagement: 78% signed up for the newsletter via tablets.

- Positive customer sentiment: 72% reported correct orders, 82% found checkout quick and secure, and 40% preferred tablets exclusively.

# Lessons Learned

 Navigation design matters: Initial layouts confused guests; simplified design improved usability.

- Training is critical: Waitstaff awareness of guest pacing directly impacted table turn times.

- Payment clarity is essential: Customers needed clear messaging about card-only payments; cash handling required streamlined processes.

- Kitchen coordination: Errors in food preparation highlighted the need for stronger BOH communication and accountability.

- Technology reliability: Pre-service testing reduced glitches significantly; proactive maintenance is key.

- Customer preferences vary: While many enjoyed tablets, some still preferred waiter interaction, suggesting hybrid models may be optimal.

# Next Steps

    Expand rollout to additional locations, applying lessons learned.

- Continue refining tablet navigation and menu design for ease of use.

- Explore hybrid service models combining tablets with waiter interaction.

- Strengthen kitchen QA processes to further reduce incorrect orders.

- Enhance customer communication about payment options and checkout flexibility (e.g., mobile pay).

- Monitor weekly technical performance to maintain

- Track customer satisfaction metrics through ongoing surveys.

# Project Documentation Archive

- [link the project proposal]

- [link the project charter]

- [link the project plan]

- [link the evaluation findings presentation]